EXHIBIT 1-C

SAMPLE MANAGEMENT PLAN FORMAT

FOR A HOUSING REHABILITATION PROJECT

ADMINISTERED WITH THE ASSISTANCE OF A CONTRACTED CONSULTANT

I.	Administrative Structure

The City of ______________ is an incorporated city with a Mayor-Council form of government.  The following persons will have lead responsibility for administering the City's FY____ Community Development Block Grant (CDBG) housing rehabilitation and neighborhood revitalization project.

Mayor ____________, as the City's chief elected official will have responsibility for all official contacts with the Montana Department of Commerce (MDOC) and will serve as the Environmental Certifying Officer. The Mayor and Town Council will have ultimate authority and responsibility for the management of project activities and expenditure of CDBG funds. The final approval of all contracts and drawdown requests will be the responsibility of the City Council.  (email ___________)

___________________, Clerk-Treasurer, as the City's chief financial officer, will be responsible for management of, and record keeping for, the CDBG funds and other funds involved in the financing of the water project. One-fourth of this position's time will be devoted to CDBG administration during the term of the project.  (email __________)

___________________, Contracted Consultant, will be designated as Project Manager and will be responsible for overall project management and insuring compliance with applicable federal and state requirements for the CDBG project. The Project Manager will serve as the City's liaison with MDOC for the project and will serve as the Labor Standards Officer. (email ____________)

___________________, City Attorney, as the City's legal counsel, will review and advise the Mayor and Council regarding any proposed contractual agreements associated with this MDOC/CDBG project and provide any other legal guidance as requested. (email ____________)

The Mayor and Clerk-Treasurer and the Consultant will the MDOC CDBG Administration Workshop (as required of all CDBG grant recipients).

II.	Project Management

A.	The Project Manager (contracted consultant) will be responsible for:

1.	Preparing the Environmental Review Record (ERR) to assure full compliance with the National and Montana Environmental Policy Acts, completion of the statutory checklist, and any other applicable environmental requirements. The Project Manager will also be responsible for preparing any legal notices required to be published for the ERR process and conducting any required public hearings or informational meetings.

2.	Preparing a request for release of funds to MDOC (upon completion of the Environmental Review).

3.	Developing a contract with DOC and assisting the City with all requirements related to effective project start-up and implementation.

4.	Establishing and maintaining complete and accurate project files and preparing all documentation and reports incidental to administration of the grant.

5.	Assuring compliance with applicable acquisition, civil rights, Section 504/ADA evaluation and labor standards requirements, including the preparation of an equal employment opportunity plan, an ADA compliance plan and a fair housing ordinance, which will be adopted by the City.

6.	Reviewing all proposed project expenditures or requests for payment to ensure their propriety and proper allocation of expenditures to the CDBG budget.

7.	In cooperation with the Clerk-Treasurer, processing payment requests and preparing drawdown requests to DOC, including the Request for Payment and Status of Funds Report and the Project Progress Report.

8.	Preparing all required performance reports and closeout documents for submittal to DOC and assist the City with the selection of an independent auditor.

9.	Attending City Council meetings to provide project status reports and representing the CDBG project at any other public meetings, as deemed necessary by the Mayor.

10.	Under the supervision and with the assistance of local officials, administering and implementing the City's CDBG housing and neighborhood revitalization project, in accordance with all applicable state, federal, and local requirements, with responsibilities to include:

- establishing, at the Consultant's expense, a local housing rehabilitation office, staffed full-time to provide complete housing rehabilitation services including:

•	assisting homeowners and landlords with applications;

•	screening applicants for eligibility;

•	inspecting homes for needed rehabilitation and making  recommendations to the project advisory committee;

•	assisting applicants with loan applications and coordinating the loan review process with the borrower and the applicant;

•	assisting recipients with contractor negotiations and bid awards;

•	preparation of contractor bid sheets; and

•	assuring title searches, credit reviews, and income verifications.

b.	in cooperation with the project advisory committee, developing a marketing strategy for the project to ensure a high level of participation by eligible households and performing public information activities, including preparation of newspaper advertisements and articles regarding the project; posters, and radio notices;

c.	negotiating with private lenders and public agencies to stimulate additional housing investment in the project area;

d.	coordinating services with other agencies, such as Montana Power, the area’s HRDC, Senior Citizens Center, and the county health and public assistance/welfare departments, to achieve maximum impact upon the needs of low and moderate income households in the project area;

e.	securing State Historic Preservation Office clearance for housing rehabilitation activities, as necessary, either by district designation or by a review of individual housing units;

f.	providing technical assistance to the City for adoption of appropriate codes for the acquisition and/or demolition of unsafe and abandoned property;

g.	conducting informational meetings for contractors and  preparing lists of eligible contractors;

h.	ensuring that proper inspections are performed, required permits are obtained, and lien waivers signed; and

i.	serving as staff for meetings of the project advisory committee.

B.	The Mayor will appoint a five-member project advisory committee to assist the City with the implementation of the housing rehabilitation project. The committee's responsibilities will include:

1.	assuring that the following certifications, plans, policies, and resolutions have been put in place:

- Hatch Act Resolution;

- Equal Employment Opportunity (EEO)/Nondiscrimination Policy;

- Drug Free Workplace Policy;

- Fair Housing Resolution; and

- Section 504 and ADA Compliance Procedures

- ADA Transition Plan

2.	assisting and providing guidance to the Project Manager relating to the implementation of the City's CDBG project;

3.	preparing terms for financial assistance including eligibility guidelines for LMI households, loan terms, interest rates, and policies on the deferral and/or forgiveness (as appropriate) of loan repayments; these policies will be adopted in final form by the City Council;

4.	reviewing applications for assistance and making recommendations on the form of assistance (loan, grant, loan/grant combination) to be provided;

5.	considering alternatives and recommending actions to be taken in the event of complaints, homeowner-contractor disputes, inadequacy of work quality, or other issues affecting the project;

6.	assisting in the marketing of the project to the low and moderate income residents of the project area; and

7.	recommending administrative policies for the project to the City Council, for its adoption.

III.	Financial Management

A.	The Clerk-Treasurer's responsibilities will be as follows:

1.	Establishing the CDBG bank account and transferring CDBG funds from that account to the town's treasury for disbursements, based on claims and supporting documents approved by the project manager, project engineer, and contractor. Since the City uses an interest bearing account for its general disbursements, a separate non-interest bearing account will be used for CDBG funds. Balances in that account will not exceed $5,000 for a period of three days.

- Entering all project transactions into the City's existing accounting system, and prepare checks/warrants for approved expenditures.

3.	With the assistance of the Project Manager, preparing the Request for Payment and Status of Funds Reports to be submitted to MDOC. All drawdown requests will be signed by two of the three following persons:  Mayor, Clerk-Treasurer, and Council President. No expenditures will be made without the approval of the Council at a regular meeting.

4.	With the assistance of the Project Manager, preparing the final financial reports for project closeout.

B.	The Project Manager will review all proposed expenditures of CDBG funds and will prepare drawdown requests, which will be signed by the officials cited above.  All disbursements will be handled in accordance with the City's established claim review procedures. Before submitting the claim to the Clerk-Treasurer, the Project Manager will attach a certification to each claim stating that the proposed expenditure is an eligible expense of the City's CDBG project and consistent with the project budget. The Council will review all claims before approving them.

C.	Financial record keeping will be done in conformance with the recommendations of MDOC’s Community Development Division as described in Chapter 4 of the CDBG Administration Manual. The original financial documents (claims with all  supporting material attached) will be retained in the City's offices.

D.	To ensure timely payment of housing rehabilitation contractors, an escrow account will be established. Withdrawals from the escrow can be made by the Clerk-Treasurer, in accordance with signed approvals by the Project Manager.

E.	Weekly timesheets will maintained by the Project Manager and the Clerk-Treasurer to document all time worked on the CDBG project.

F.	The City's housing and neighborhood revitalization project will generate some CDBG “Program Income” from loan repayments and the sale of the sites of unsafe, abandoned property acquired and demolished through the CDBG project. Any Program Income received from these sources will be deposited in the City's established community development fund for CDBG Program Income. Any Program Income received prior to project closeout will be used to assist additional LMI households with housing rehabilitation needs. The use of Program Income received after project closeout will be limited to those activities eligible under the CDBG program and will be determined at the discretion of the City Council.

A sample Project Implementation Schedule, which outlines the basic steps and timetable involved in the management of the project, can be found in the CDBG Application Guidelines or by contacting the Department project liaison for fillable forms. A general description/outline is provided below.

- SAMPLE PROJECT IMPLEMENTATION SCHEDULE

A.	START-UP

1.	Attend MDOC Workshop	City Council	May             20xx

2.	Update Management Plan, Budget, &  	Council & Project Mg.	March 	20xx

Schedule for the CDBG contract

3.	Establish Public Facilities Project Files  	Project Manager	May 	20xx

4.	Award Engineering Contract	City Council	March 	20xx

5.	Determine Audit Requirements 	Project Manager 	May  	20xx

6.	Schedule Local Govt Audit(s)	Council & Project Mg.   	June 	20xx

7.	Authorize Final Design 	City Council	March	20xx

8.	Complete ERR/Submit to CDBG 	Project Manager 	May 	20xx

9.	Secure MDOC Approval of RROF  	Project Manager 	June 	20xx

10.	Complete Final Design  	Project Engineer	April   	20xx

B.	IMPLEMENTATION

1.	Submit First Drawdown Request	Clerk-Treasurer	June 	20xx

2.	Present Final Design for Review	Project Engineer	April 	20xx

3.	Complete Final Plans 	Project Engineer	April  	20xx

4.	Submit Plans to DEQ and CDBG	Project Engineer	May	20xx

5.	Secure Wage Rate Determination 	Project Engineer	June 	20xx

6.	Prepare Construction Bid Documents   	Project Engineer	June 	20xx

and Secure CDBG Approval

7.	Advertise For Bids	City Council	June 	20xx

8.	Bid Opening  	Project Engineer	July             20xx

9.	Clearance of Low Bidders 	Project Engineer	July             20xx

10.	Bid Award 	City Council	July 	20xx

C.	CONSTRUCTION

1.	Pre-construction Conference	Project Engineer	August 	20xx

2.	Submit Compliance Documents  	Project Engineer	August 	20xx

3.	Start Construction	Project Engineer	Sept 	20xx

4.	Weekly Labor Standards Monitoring	Project Manager 	Sep-Dec 	20xx

5. 	CDBG on-site monitoring/review 	CDBG Liaison	October	20xx

6.	Submit Drawdowns (with Progress	Project Manager	Ongoing

Reports) & Qrtrly Progress Reports	Clerk-Treasurer	As Needed

7.	Final Inspection 	Project Engineer	Dec 	20xx

8.	Final Payment to Contractor  	City Council	Jan 	20xx

9.	In-service System Training	Project Engineer	Dec 	20xx

10.	Connect Households to System	Project Engineer	Nov 	20xx

11.	Final Payment to Engineer 	City Council	Feb  	20xx

D.	CLOSEOUT

1.	Project Closeout Begins  	Project Manager 	Dec 	20xx

2.	Project Completion Report 	Project Manager 	Jan 	20xx

3.	Audits are conducted/reviewed	Project Manager & CDBG	Sept	20xx